## Data dictionary
Contacts Databse Dictionary
Table Name | Column Name | Type | Required | Primary Key | Foreign Key
CONTACT | Create Third
| CID | INT | yes | yes | no | Auto Inc.
| CFName | varchar(30) | yes | no | no
| CLName | varchar(30) | yes | no | no
| CDispName | varchar(30) | yes | no | no | Do we really need this?
| CImage | varchar(45) | no | no | no
| GID | INT | no | no | YES
| UID | INT | yes | no | YES
PHONE | Create Fourth |  |  |  |  | Do we want to have different types: HOME, BUSINESS, CELL, etc?
| PID | INT | yes | yes | no | Auto Inc.
| Pphone | char(10) | yes | no | no | force to have 10 characters?, or allow less for local.
| CID | INT | yes | no | YES
EMAIL | Create Fifth
| EID | INT | yes | yes | no | Auto Inc.
| CEmail | varchar(40) | yes | no | no
| CID | INT | yes | no | YES
ADDRESS | Create Sixth |  |  |  |  | Do we want to have different types: HOME, BUSINESS
| AID | INT | yes | yes | no | Auto Inc.
| Astreet | varchar(40) | yes | no | no
| Acity | varchar(40) | yes | no | no
| Astate | char(2) | yes | no | no
| Azip | char(5) | yes | no | no
| CID | INT | yes | no | YES
GROUP | Create Second |  |  |  |  | I think we should consider allowing multiple contacts in each group...
| GID | INT | yes | yes | no | Auto Inc.
| Gname | varchar(30) | yes | no | no
| UID | INT | yes | no | YES
USER | Create First
| UID | INT | yes | yes | no | Auto Inc.
| UserName | varchar(30) | yes | no | no | Do we want to have the username be an e-mail? For potential future recovery purposes?
| Upassword | varchar(40) | yes | no | no | Do we need to have more characters - i.e. are we going to mask the password?

## schedule
Marco Task | Number | Task | Dependencies | Start Date | Finish Date | Assignment | Done?
Initial Start-up | 1 | Set up Git-HUB |  | 2014-04-08 | 2014-04-10 | All
| 2 | ERD for Database |  | 2014-04-08 | 2014-04-10 | Jay
| 3 | Approval of ERD - Milestone |  |  | 2014-04-10 | All
| 4 | Schedule/Tasks for Project |  | 2014-04-08 | 2014-04-10 | Deb
| 5 | template for project --> web and mobile |  | 2014-04-08 | 2014-04-10 | Marc
| 6 | Get initial classes setup |  | 2014-04-08 | 2014-04-10 | Deb
| 7 | Set up Database | 2, 3 | 2014-04-10 | 2014-04-11 | Jay
| 8 | Set up Dummy-data in Database | 7 | 2014-04-10 | 2014-04-11
Design pages: | 9 | index.php / with header and footer includes, login and/or create new user |  | 2014-04-10 | 2014-04-15
| 10 | contacts.php --> shows list of all contacts / potential to search / and add contact |  | 2014-04-10 | 2014-04-15
| 11 | detail.php --> shows the detail (including map) of a selected contact / can delete a phone/email/address, or add a phone/email/address. |  | 2014-04-10 | 2014-04-15
| 12 | Approval of Designed pages - Milestone |  |  | 2014-04-15 | All
Develop functionality: | 13 | login / session capability and put into header |  | 2014-04-15 | 2014-04-17
| 14 | sort contacts by alphabet / print out in that order |  | 2014-04-11 | 2014-04-17
| 15 | research / set up code to upload image taken by mobile phone picture (add picture sends to mobile camera) |  | 2014-04-10 | 2014-04-17
| 16 | research / set up code to add new image by file upload |  | 2014-04-10 | 2014-04-17
| 17 | set up code to add new user / contact / phone / email / address / group |  | 2014-04-10 | 2014-04-15
| 18 | set up code to edit new user / contact / phone / email / address / group |  | 2014-04-10 | 2014-04-15
| 19 | set up code to delete new user / contact / phone / email / address / group |  | 2014-04-10 | 2014-04-15
| 20 | set up code to print all contacts by UID in post? Or however session works |  | 2014-04-15 | 2014-04-17
| 21 | set up code to print all contact detail by CID num in post |  | 2014-04-11 | 2014-04-15
| 22 | set up code for geocoding map from address |  | 2014-04-10 | 2014-04-15
| 23 | set up code for geocoding map for specific contact via CID num in post |  | 2014-04-15 | 2014-04-17
| 24 | Approval of Functionality - Milestone |  |  | 2014-04-17 | All
Put functionality into pages: | 25 | index.php / login, create new user, direct to contacts list / maintain header footer functionality |  | 2014-04-15 | 2014-04-24
| 26 | contacts.php / print out of sorted contacts w/ search and add contact which directs to detail |  | 2014-04-15 | 2014-04-22
| 27 | contacts.php / pagination |  | 2014-04-22 | 2014-04-24
| 28 | detail.php / add new contact or modify pulled up contact. (add/edit/delete detail info) |  | 2014-04-15 | 2014-04-24
| 29 | Approval of Rough Site - Milestone |  |  | 2014-04-24 | All
Add in extra functionality | 30 | tweak layout, make pretty, modify css as needed, add in little extras.
| 31 | cross check to not add new user if one exists w/ same name |  | If time
| 32 | cross check to not add new contact if one exitst w/ same name |  | If time
| 33 | recovery / resetting of password